## Sheet1
Task | Description | Dependency | Duration in days
A | System analysis | start | 2
B | System Desgin | A | 2
C | Database Implementation | B | 1
D | Front end Implementation | C,B | 4
E | Back end Implementation | D,C | 4
F | Testing | E | 1